## Sheet1
FRIENDLY ASSISTED LIVING FACILITY (RACI) |  |  | Fred | Construction Project Manager | COO | CFO | IS Director | Vp of Business Development | Medical Director
1. FACILITY PHASE
| 1.1 | Building Design | I |  | S
| 1.2 | Construciton of the Facility | I | R
2. FINANCIAL
| 2.1 | Create budgets for each project area | C |  |  | R |  | C
| 2.2 | Create payroll and accoutning systems for facility | C |  |  | R | C | C
3. BUSINESS
| 3.1 | Create marketing plan for community and hospital staff | C |  | C |  |  | R
| 3.2 | Organizing a groundbreaking event | I |  | C |  |  | R
| 3.3 | Identify all government regulations and industry standards | R | C | C | C | C | C | C
4. FUNCTIONALITY
| 3.1 | Develop management structure for the facility | R |  | C
| 3.2 | Define staffing | C |  | C |  | C |  | C
| 3.3 | Define food service needs |  |  | R |  |  |  | S
| 3.4 | Define housekeeping needs |  |  | R |  |  |  | S
| 3.5 | Define policy needs | C |  | R |  |  |  | C
| 3.6 | Procedure development | C |  | R |  |  |  | C
| 3.7 | Define and setup telecommunications and information systems for facility |  |  | C |  | R |  | C
| 3.8 | Design assessment tools for determinging resisdents level of medical needs |  |  | C |  |  |  | R